{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Kabelliste"],"read":"whole","date_system":"1900"}

{"sheet":"Kabelliste","index":0,"n_rows":220,"n_cols":18,"rows_kept":220,"merged":[[0,0,0,17],[2,5,2,17],[3,5,3,6],[4,5,4,6],[5,5,5,6],[6,5,6,6],[214,0,214,17]]}
["Kabelliste"]
[]
["Projektname","Verkabelung Neubau Bürotrakt",{"$nulls":3},"Projektübersicht / Kennzahlen"]
["Standort","Gebäude A, 3. OG",{"$nulls":3},"Anzahl Kabel insgesamt:",null,{"$f":"COUNTA(A11:A210)","v":8}]
["Projektleiter","Max Mustermann",{"$nulls":3},"Länge gesamt (m):",null,{"$f":"SUM(H11:H210)","v":{"v":154,"d":"154.0"}}]
["Datum","2025-11-24",{"$nulls":3},"Anzahl Kabel pro Status:"]
["Version","v1.0",{"$nulls":3},"Letzte Aktualisierung:",null,{"$f":"TODAY()","v":"2025-11-24"}]
[]
[]
["Kabel-ID","Kabelbezeichnung","Kabeltyp","Kategorie / System","Querschnitt (mm²)","Aderzahl","Farbcode","Länge (m)","Start-Standort (Raum/Gerät)","Start-Anschluss / Port","End-Standort (Raum/Gerät)","End-Anschluss / Port","Schaltkreis / System-ID","Zuordnung (Anlage/Bereich)","Status","Prüfdatum","Verantwortlich","Bemerkungen / Link Datenblatt"]
["K-001","Patchkabel Cat6a 3m","Datenkabel","IT / Netzwerk",null,8,"blau",{"v":3,"d":"3.0"},"Serverraum R1","Patchpanel 1 Port 01","Büro 3.12","Datendose 3.12-01","VLAN10","Bürotrakt Nord","getestet","2025-11-10","T. Schneider","Link: https://example.com/cat6a"]
["K-002","Patchkabel Cat6a 5m","Datenkabel","IT / Netzwerk",null,8,"blau",{"v":5,"d":"5.0"},"Serverraum R1","Patchpanel 1 Port 02","Büro 3.15","Datendose 3.15-01","VLAN20","Bürotrakt Nord","verlegt",null,"T. Schneider"]
["K-003","NYM-J 3x1,5 Zuleitung Licht","Stromkabel","Beleuchtung",1.5,3,"braun/blau/grün-gelb",18.5,"Verteilerkasten EG","LS-Schalter L12","Flur 3.OG","Abzweigdose F3-01","Stromkreis 12","Treppenhaus","geplant",null,"E. Müller","Leitung noch zu verlegen"]
["K-004","NYM-J 5x2,5 Steckdosen","Stromkabel","Starkstrom",2.5,5,"braun/schwarz/grau/blau/grün-gelb",{"v":22,"d":"22.0"},"Verteilerkasten EG","LS-Schalter L18","Büro 3.20","Steckdosenring B3.20","Stromkreis 18","Bürotrakt Nord","verlegt",null,"E. Müller"]
["K-005","Steuerleitung J-Y(St)Y 2x2x0,8","Steuerkabel","Gebäudeautomation",0.8,4,"rot/blau/weiß/gelb",{"v":30,"d":"30.0"},"Technikraum GA","Klemme K-GA-05","Dachzentralgerät","Klemme K-DZ-02","GA-Bus 1","Lüftungsanlage","getestet","2025-11-18","S. Wagner"]
["K-006","Mikrofonkabel Bühne L","Audio/Video","Bühnentechnik",null,2,"schwarz",{"v":15,"d":"15.0"},"Bühne vorne links","Stagebox L-01","FOH-Platz","Mischpult Kanal 1","AudioBus1","Veranstaltungssaal","getestet","2025-11-05","J. Becker"]
["K-007","Lautsprecherkabel rechts","Audio/Video","Bühnentechnik",null,2,"rot/schwarz",{"v":18,"d":"18.0"},"Endstufe Rack","Out R","Lautsprecher rechts","Speaker R","AudioBus2","Veranstaltungssaal","außer Betrieb","2024-09-01","J. Becker","Lautsprecher aktuell außer Betrieb"]
["K-008","Busleitung KNX","Steuerkabel","Gebäudeautomation",null,2,"grün",42.5,"Technikraum GA","KNX-Klemme TR1","Sensoren Flur 3.OG","KNX-Klemme F3","KNX-Linie 1","Flure","geplant",null,"S. Wagner","Geplante Erweiterung 2026"]
{"$rows_empty":196}
["Legende / Hinweise zur Kabelliste"]
["• Kabel-ID: Eindeutige Kennzeichnung je Kabel (z.B. K-001)."]
["• Status „geplant“: Kabel ist vorgesehen, aber noch nicht verlegt."]
["• Status „verlegt“: Kabel ist physisch installiert."]
["• Status „getestet“: Kabel ist verlegt und erfolgreich geprüft."]
["• Status „außer Betrieb“: Kabel ist außer Nutzung, bleibt aber dokumentiert."]